## Sheet1
Time | 21.10.2019-01.11.2019 | 02.11.2019-17.11.2019 | 17.11.2019-22.11.2019 | 23.11.2019-13.12.2019 | 13.11..2019-20.11.2019
Work
Writing Literature Recuirements Document,Algorithms and Literature Reserach
Writing/Researching SRS Document + project webpage
Finishing last changes of SRS document +Start research on SDD document
Writing/Researching SDD
Project Report + Presentation